## Gantt
Family Health Track Interface | [29 empty] | Legend:
[30 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
|  | Project Start Date: |  | 2020-11-02
|  | Display Week: |  | 1 |  | November
 | time axis 2020-11-02 to 2020-12-20
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
Milestone Description | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Sprint 1
Learning - React framework | Med Risk | Parul |  | 2020-11-02 | 7
Setup Skeleton - Fronend | Med Risk |  |  | 2020-11-02 | 7
Setup Skeleton - Backend | Med Risk |  |  | 2020-11-02 | 7
Setup Database Postgres (Docker) | Med Risk |  |  | 2020-11-02 | 7
Setup Pipeline | Milestone |  |  | 2020-11-06 | 3 | bar: Week 1 F to Week 1 S
Sprint 2
Prepare Test Patients | Low Risk |  |  | 2020-11-09 | 5
Code Main Screen - Search Components UI | Med Risk |  |  | 2020-11-09 | 7
Code Main Screen - Search Backend API | Med Risk |  |  | 2020-11-09 | 7
Setup FHIR Server Service Invoker | Med Risk |  |  | 2020-11-09 | 7
Integrate Basic Flow (Frontend - Backend) | Milestone |  |  | 2020-11-14 | 2 | bar: Week 2 S to Week 2 S
Sprint 3
Code Main Screen - Patient Card UI | High Risk |  |  | 2020-11-16 | 6
Code Main Screen - Patient Info API | Med Risk |  |  | 2020-11-16 | 6
Integrate Main screen UI and Backend | Milestone |  |  | 2020-11-21 | 2 | bar: Week 3 S to Week 3 S
Testing and Bug Fixes | Low Risk |  |  | 2020-11-21 | 2
Sprint 4
Code Login Screen UI and Backend | Med Risk |  |  | 2020-11-23 | 3
Code Signup Screen UI and Backend | Low Risk |  |  | 2020-11-23 | 3
Final Integration, Testing and Bug Fixes | High Risk |  |  | 2020-11-25 | 4
Final Documentation | Milestone |  |  | 2020-11-26 | 4 | bar: Week 4 T to Week 4 S
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.